## Slide 1
WEEK 4 • TEAM SIGN-OFF
Australian Mammal
Distribution Explorer
Risk register • SMART goals • Kanban • RTM
Status snapshot: 11 August 2026
Sign-off target: 28 August 2026
Shu Sato • Kok Hee Tan • Nethra Yamala • William Koo
Australian Mammal Distribution Explorer | FIT3163 Group 15
1/5
Notes: [Sources]
- pitch/Mid-sem Pitch.pdf, pages 1-2 (Week 4 sign-off requirements).
- README.md at origin/main (project name and team).

## Slide 2
RISK REGISTER
The largest delivery risk is the data-to-map handoff
ID | Risk | P | I | Rating | Current control / contingency
R1 | Map payload is too large for a responsive demo | 4 | 5 | Extreme | Pre-aggregate and cluster; test a smaller sample before full integration.
R2 | Dataset schema or versions drift between Drive and the app | 4 | 4 | Extreme | Freeze a named snapshot, checksum it, and agree the frontend schema before 17 Aug.
R3 | Ready work concentrates on too few people | 3 | 4 | High | Assign each pulled card, keep WIP at 2, and time-box review hand-offs.
R4 | Optional modelling displaces the core MVP | 3 | 4 | High | Deliver five-species map and time flow first; retain MaxEnt as conditional scope.
Immediate control: freeze the data contract before frontend work begins on 17 August.
Australian Mammal Distribution Explorer | FIT3163 Group 15
2/5
Notes: [Sources]
- Jira KAN board snapshot, 11 Aug 2026 (statuses, dates, WIP and assignments).
- Google Drive dataset metadata (GeoJSON 98,200,569 bytes; CSV 29,118,674 bytes).
- pitch/sign-off example.pdf, pages 24-25 (prior-semester risk framing).

## Slide 3
SMART GOALS
Four dated goals carry the project to the Week 6 pitch
G1
14 AUG
Publish the five-species frozen snapshot
Manifest, source/licence metadata, validation checks and reproducible cleaning steps are complete.
KAN-24 • Data foundation
G2
21 AUG
Demonstrate the UI and map skeleton
All five species appear in the selector and the attributed MapLibre base map loads from a clean checkout.
KAN-32 + KAN-36 • Core explorer
G3
28 AUG
Show one traceable end-to-end sample
One species dataset reaches the map with loading, empty and invalid-data states documented for sign-off.
KAN-40 + KAN-81 • Week 4 checkpoint
G4
11 SEP
Pitch a tested vertical slice
Species selection, map and one time interaction work together with CI and test evidence ready for questions.
KAN-26 + KAN-83 • Week 6 pitch
Australian Mammal Distribution Explorer | FIT3163 Group 15
3/5
Notes: [Sources]
- Jira issue dates and acceptance criteria: KAN-24, KAN-26, KAN-32, KAN-36, KAN-40, KAN-81 and KAN-83.
- pitch/Mid-sem Pitch.pdf, page 2 (SMART goals must link to milestones/deliverables).

## Slide 4
UPDATED KANBAN
The board now shows a controlled two-item WIP
Chart: 
| Done | Active | Ready | Backlog
Cards | 4 | 2 | 9 | 52
67
total cards
CURRENT FOCUS
• KAN-17 Data pipeline epic
• KAN-24 Frozen ALA snapshot
NEXT PULL
Environmental data, species selector,
and MapLibre base map are Ready.
Policy: pull from Ready, assign before starting, and keep no more than two active cards.
Australian Mammal Distribution Explorer | FIT3163 Group 15
4/5
Notes: [Sources]
- Jira project KAN JQL snapshot, 11 Aug 2026: 4 Done, 2 In Progress, 9 Ready, 52 Backlog.
- Jira KAN-17, KAN-24, KAN-25, KAN-32 and KAN-36 (current and next work).
- pitch/sign-off example.pdf, page 14 (Kanban flow and WIP control).

## Slide 5
REQUIREMENTS TRACEABILITY MATRIX
High-priority requirements are fully traceable
ID | Requirement | Priority | Delivery | Verification | Current
SR-1 | Choose one of five MVP mammals | Must | KAN-32, KAN-26 | Functional selection and state test | Ready
SR-2 | Map records; filter by year, month and season | Must | KAN-36/40/44/48 | Functional and integration tests | Ready / planned
SR-3 | Show state, monthly and weather summaries | Should | KAN-25, KAN-26 | Data validation and linked-view test | Ready
SR-4 | Show source, snapshot, count and licence | Must | KAN-24, KAN-26 | Manifest and UI content review | In progress
NFR-1 | Reproducible checks and frozen data | Must | KAN-23, KAN-24 | CI plus rerun from frozen snapshot | Part done
Sign-off focus: protect Must scope and attach evidence as each Jira delivery moves to Done.
Australian Mammal Distribution Explorer | FIT3163 Group 15
5/5
Notes: [Sources]
- pitch/sign-off example.pdf, page 10 (significant requirements and user value).
- Jira delivery and acceptance criteria: KAN-23 to KAN-26, KAN-32, KAN-36, KAN-40, KAN-44 and KAN-48.
- pitch/Mid-sem Pitch.pdf, page 2 (RTM sign-off expectations).